## Project
MeetingCycle | DesignChangeCycle | ProductionRateChange | QualityCheck | TaskSelectionFunction | PriorityChange | CollisionInformationExchnage
7 | 30 | 1 | 1 | 1 | 0 | 1

## Sub
SubName
Electricity
Gravel
Partition
Plumbing
Tiling

## WorkMethod
SubName | WorkMethod | InitialProductionRate | QualityRate | PerformanceStd
Gravel | Gravel base layer | 34 | 0.7 | 5
Plumbing | Pipes in the floor | 69 | 0.7 | 5
Electricity | Electric conduits in the floor | 51 | 0.7 | 8
Tiling | Floor tiling | 62 | 0.7 | 9
Partition | Partition phase 1 | 110 | 0.7 | 12
Plumbing | Pipes in the wall | 37 | 0.7 | 9
Partition | Partition phase 2 | 102 | 0.7 | 11
Electricity | Electric conduits in the wall | 41 | 0.7 | 2
Partition | Partition phase 3 | 64 | 0.7 | 4
Tiling | Wall tiling | 27 | 0.7 | 2

## WorkMethodDependency
PredecessorWorkMethod | SuccessorWorkMethod
Gravel base layer | Pipes in the floor
Gravel base layer | Electric conduits in the floor
Pipes in the floor | Floor tiling
Electric conduits in the floor | Floor tiling
Partition phase 1 | Pipes in the wall
Pipes in the wall | Partition phase 2
Partition phase 2 | Electric conduits in the wall
Electric conduits in the wall | Partition phase 3
Partition phase 3 | Wall tiling

## WorkSpace
Floor | InitialPriority
1 | 5
2 | 4
3 | 3
4 | 2
5 | 1

## Task
WorkMethod | Floor | InitialQty | DesignChangeVariation
Gravel base layer | 1 | 170 | 17
Pipes in the floor | 1 | 100 | 10
Electric conduits in the floor | 1 | 80 | 8
Floor tiling | 1 | 720 | 72
Partition phase 1 | 1 | 750 | 75
Pipes in the wall | 1 | 190 | 19
Partition phase 2 | 1 | 20 | 2
Electric conduits in the wall | 1 | 180 | 18
Partition phase 3 | 1 | 200 | 20
Wall tiling | 1 | 290 | 29
Gravel base layer | 2 | 170 | 17
Pipes in the floor | 2 | 100 | 10
Electric conduits in the floor | 2 | 80 | 8
Floor tiling | 2 | 720 | 72
Partition phase 1 | 2 | 750 | 75
Pipes in the wall | 2 | 190 | 19
Partition phase 2 | 2 | 20 | 2
Electric conduits in the wall | 2 | 180 | 18
Partition phase 3 | 2 | 200 | 20
Wall tiling | 2 | 290 | 29
Gravel base layer | 3 | 170 | 17
Pipes in the floor | 3 | 100 | 10
Electric conduits in the floor | 3 | 80 | 8
Floor tiling | 3 | 720 | 72
Partition phase 1 | 3 | 750 | 75
Pipes in the wall | 3 | 190 | 19
Partition phase 2 | 3 | 20 | 2
Electric conduits in the wall | 3 | 180 | 18
Partition phase 3 | 3 | 200 | 20
Wall tiling | 3 | 290 | 29
Gravel base layer | 4 | 170 | 17
Pipes in the floor | 4 | 100 | 10
Electric conduits in the floor | 4 | 80 | 8
Floor tiling | 4 | 720 | 72
Partition phase 1 | 4 | 750 | 75
Pipes in the wall | 4 | 190 | 19
Partition phase 2 | 4 | 20 | 2
Electric conduits in the wall | 4 | 180 | 18
Partition phase 3 | 4 | 200 | 20
Wall tiling | 4 | 290 | 29
Gravel base layer | 5 | 170 | 17
Pipes in the floor | 5 | 100 | 10
Electric conduits in the floor | 5 | 80 | 8
Floor tiling | 5 | 720 | 72
Partition phase 1 | 5 | 750 | 75
Pipes in the wall | 5 | 190 | 19
Partition phase 2 | 5 | 20 | 2
Electric conduits in the wall | 5 | 180 | 18
Partition phase 3 | 5 | 200 | 20
Wall tiling | 5 | 290 | 29