## Project
MeetingCycle | DesignChangeCycle | ProductionRateChange | QualityCheck | TaskSelectionFunction | PriorityChange | CollisionInformationExchange
0 | 30 | 1 | 1 | 1 | 0 | 0
0 | 30 | 1 | 1 | 0 | 0 | 0
0 | 30 | 1 | 1 | 1 | 0 | 1
0 | 30 | 1 | 1 | 0 | 0 | 1

## Sub
SubName
Electricity
Gravel
Partition
Plumbing
Tiling

## WorkMethod
SubName | WorkMethod | InitialProductionRate | QualityRate | PerformanceStd
Gravel | Gravel base layer | 1 | 0.9 | 0.1
Plumbing | Pipes in the floor | 1 | 0.9 | 0.1
Electricity | Electric conduits in the floor | 1 | 0.9 | 0.1
Tiling | Floor tiling | 1 | 0.9 | 0.1
Partition | Partition phase 1 | 1 | 0.9 | 0.1
Plumbing | Pipes in the wall | 1 | 0.9 | 0.1
Partition | Partition phase 2 | 1 | 0.9 | 0.1
Electricity | Electric conduits in the wall | 1 | 0.9 | 0.1
Partition | Partition phase 3 | 1 | 0.9 | 0.1
Tiling | Wall tiling | 1 | 0.9 | 0.1

## WorkMethodDependency
PredecessorWorkMethod | SuccessorWorkMethod
Gravel base layer | Pipes in the floor
Gravel base layer | Electric conduits in the floor
Pipes in the floor | Floor tiling
Electric conduits in the floor | Floor tiling
Partition phase 1 | Pipes in the wall
Pipes in the wall | Partition phase 2
Partition phase 2 | Electric conduits in the wall
Electric conduits in the wall | Partition phase 3
Partition phase 3 | Wall tiling

## WorkSpace
Floor | InitialPriority
1 | 5
2 | 4
3 | 3
4 | 2
5 | 1

## Task
WorkMethod | Floor | InitialQty | DesignChangeVariation
Gravel base layer | 1 | 5 | 0.5
Pipes in the floor | 1 | 5 | 0.5
Electric conduits in the floor | 1 | 5 | 0.5
Floor tiling | 1 | 5 | 0.5
Partition phase 1 | 1 | 5 | 0.5
Pipes in the wall | 1 | 5 | 0.5
Partition phase 2 | 1 | 5 | 0.5
Electric conduits in the wall | 1 | 5 | 0.5
Partition phase 3 | 1 | 5 | 0.5
Wall tiling | 1 | 5 | 0.5
Gravel base layer | 2 | 5 | 0.5
Pipes in the floor | 2 | 5 | 0.5
Electric conduits in the floor | 2 | 5 | 0.5
Floor tiling | 2 | 5 | 0.5
Partition phase 1 | 2 | 5 | 0.5
Pipes in the wall | 2 | 5 | 0.5
Partition phase 2 | 2 | 5 | 0.5
Electric conduits in the wall | 2 | 5 | 0.5
Partition phase 3 | 2 | 5 | 0.5
Wall tiling | 2 | 5 | 0.5
Gravel base layer | 3 | 5 | 0.5
Pipes in the floor | 3 | 5 | 0.5
Electric conduits in the floor | 3 | 5 | 0.5
Floor tiling | 3 | 5 | 0.5
Partition phase 1 | 3 | 5 | 0.5
Pipes in the wall | 3 | 5 | 0.5
Partition phase 2 | 3 | 5 | 0.5
Electric conduits in the wall | 3 | 5 | 0.5
Partition phase 3 | 3 | 5 | 0.5
Wall tiling | 3 | 5 | 0.5
Gravel base layer | 4 | 5 | 0.5
Pipes in the floor | 4 | 5 | 0.5
Electric conduits in the floor | 4 | 5 | 0.5
Floor tiling | 4 | 5 | 0.5
Partition phase 1 | 4 | 5 | 0.5
Pipes in the wall | 4 | 5 | 0.5
Partition phase 2 | 4 | 5 | 0.5
Electric conduits in the wall | 4 | 5 | 0.5
Partition phase 3 | 4 | 5 | 0.5
Wall tiling | 4 | 5 | 0.5
Gravel base layer | 5 | 5 | 0.5
Pipes in the floor | 5 | 5 | 0.5
Electric conduits in the floor | 5 | 5 | 0.5
Floor tiling | 5 | 5 | 0.5
Partition phase 1 | 5 | 5 | 0.5
Pipes in the wall | 5 | 5 | 0.5
Partition phase 2 | 5 | 5 | 0.5
Electric conduits in the wall | 5 | 5 | 0.5
Partition phase 3 | 5 | 5 | 0.5
Wall tiling | 5 | 5 | 0.5